## backlog
Endless Runner Backlog
Members: | Rozanna Abramtsis, Brianna Rentfrow, Rajan Perry
Task | Description | Priority | Member | Status | Start Date | Complete Date | Comments
Backlog Set Up | Copy and start the backlog for the group | 4 | Rozanna Abramtsis | Completed | 2021-10-02 | 2021-10-02
Biweekly 1 - 10/03 | Form group and turn in backlog version 1 | 4 | All | Completed | 2021-10-02 | 2021-10-02
Ideation | Agree on idea | 1 | All | Completed | 2021-10-15 | 2021-10-15 | Endless Runner
| Split up workload, set up work schedule | 3 | All | Completed | 2021-10-15 | 2021-11-14 | researching how to implement game to split tasks
| Research | 2 | All | Completed | 2021-10-15 | 2021-11-14
| Researching How to Make a Game in Godot | 3 | Rajan Perry | Completed | 2021-10-15 | 2021-10-15 | Found some Youtube tutorials and documentation
| Choose theme of game | 3 | All | Completed | 2021-10-15 | 2021-10-16
| Start concept art | 3 | Brianna Rentfrow | Completed | 2021-10-15 | 2021-10-16 | Finished concepts, moved on to art stage
| Start navigation / work flow of app | 3 | All | Completed | 2021-10-15 | 2021-11-14
Biweekly 2 - 10/18 | Have an idea, start to design user interface / navigation flow | 4 | All | Completed | 2021-10-15 | 2021-10-15 | We are going to make an Endless Runner game. We have an idea for the home screen.
Biweekly 3 - 10/31 | submit report | 4 | All | Completed | 2021-10-16 | 2021-10-31
| choose game engine software | 1 | All | Completed | 2021-10-16 | 2021-11-04 | We are using Godot
Biweekly 4 - 11/14 | Have version ready to be tested, some functionalities ok | 1 | All | Completed | 2021-11-05 | 2021-11-14
| A rough draft, at least UI implemented | 4 | All | Completed | 2021-11-05 | 2021-11-14
| art | 3 | Brianna Rentfrow | Completed | 2021-11-15 | 2021-11-27 | Completed art- characters, backgrounds, UI buttons, etc.
Biweekly 5 - 11/28 | Have working version, just need final touch-ups / documentation | 1 | All | Completed | 2021-12-02 | 2021-12-08
| implement project | 1 | All | Completed | 2021-11-17 | 2021-12-08
| UI art | 1 | All | Completed | 2021-12-03 | 2021-12-06
| create apk for the first peer review | 1 | All | Completed | 2021-11-30 | 2021-12-01 | godot version 3.4 creates APK for API 30 not API 29
| need to create apk for api 29 not api 30 | 1 | All | Completed | 2021-12-01 | 2021-12-08 | fixed it!!!
| add to readme | 1 | All | Completed | 2021-12-08 | 2021-12-08 | finished adding to Game Play section
Project code / slides due - 12/10 | Have all documentation, code, presentation slides completed and turned in | 1 | All | Completed | 2021-12-02 | 2021-12-08
Project Presentation - 12/14 | 12:15-2:30pm - present project to the class | 1 | All | In Progress | 2021-12-02

## notes
endless runner tutorials
https://www.youtube.com/watch?v=5iFOYfpKOfs&list=PL2EfDMM6n_LYJdzaOQ5jZZ3Dj5L4tbAuM&index=5
https://www.youtube.com/watch?v=aTT4GfojkHA
https://developer.android.com/games/guides
https://www.youtube.com/playlist?list=PL9FzW-m48fn2jlBu_0DRh7PvAt-GULEmd
https://www.youtube.com/playlist?list=PLsk-HSGFjnaFutTDzgik2KMRl6W1JxFgD
TODOs
research | art work / sprites
how to implement endless runner
etc.
work division | Brianna | artwork
coding - sprite sheets
| Rozanna | research endless runner
| Raj | research endless runner
research mimicing game engine in android studio

## Utils (hidden)
Priority | Status | Member | All | Rozanna Abramtsis | Brianna Rentfrow | Rajan Perry
1 | Waiting
2 | Not Started
3 | In Progress
4 | Completed